## README
FHI 360 - NGA MSNA 2026 accessibility report
Overview
This file lists every ward (and, on the second sheet, every individual cluster) currently assigned to your organisation under the NGA MSNA 2026 sampling design, so you can tell us where your teams are having trouble collecting data and why. We use this to decide how to respond - drawing a replacement cluster where needed - and to correctly document, in our final reporting, which areas' we were able to collect from and which we weren't. Accurate, complete reporting from you feeds directly into that documentation.
Assigned to you: 22 wards, 39 clusters
What to do
1 | Open the 'Ward Accessibility' sheet first - this is your main report, one row per ward you have clusters in. It's pre-filled with every ward/LGA combination assigned to you; you don't need to add or remove rows. Rows are sorted within each LGA by Total target HHs, largest first, so your main wards come before any small border cases.
2 | A row with a very small Total target HHs figure (1-2) usually means a border case - GRID3 and OCHA/COD boundaries don't always agree exactly, so a small part of one of your clusters can fall just inside a ward you don't otherwise work in. This is expected, not an error - please still report on it like any other row if it's genuinely inaccessible. If a row also shows 'Yes' under 'Ward spans multiple LGAs', see that row's Note for what part of the ward is actually yours to report on.
3 | For each ward, set Accessible (Y/N). Leave a ward's row otherwise blank if there's no issue there.
4 | For any ward marked 'No', pick the closest-fitting Reason category from the dropdown (use 'Other' plus a note if none fit), and add specific Reason notes - e.g. 'active clashes reported near [location] in the past week' is far more useful to us than just 'insecure'.
5 | If you know it, fill in roughly what % of the target sample you were able to achieve in that ward before stopping - even a rough estimate helps, and please don't leave this blank if the true answer is 0%.
6 | Only use the 'Cluster Accessibility' sheet (second tab) for a problem specific to ONE site/HH within an otherwise-fine ward - and only once you've already worked through that cluster's reserve/replacement households and they weren't enough to cover it. Don't use this sheet before exhausting your reserve list for that cluster, and don't use it as a second way to report the same ward-wide issue already captured on the first sheet.
7 | IMPORTANT: please review your ENTIRE coverage area in one pass before sending this back to us, rather than reporting a few wards now and more later - this significantly cuts down the back-and-forth rounds we need with you. If genuinely new information comes in afterwards, send an updated copy of the FULL sheet (not just the changed rows) with a new Date reported - we track changes over time by date, so we don't need you to tell us what changed, just the current full picture.
Which sheet do I use?
Sheet | Use for
Ward Accessibility | Your main report. Use for any access problem affecting a ward generally - insecurity, flooding/terrain, population displacement, denied access, etc.
Cluster Accessibility | Secondary/detail only. Use ONLY for a problem specific to one site/HH, not the surrounding ward, and only after that cluster's reserve/replacement households were already used and weren't enough.

## Ward Accessibility
State | LGA | Ward (GRID3) | Ward (OCHA/COD) | Ward spans multiple LGAs (Y/N) | Other LGA(s) sharing this ward | Note | Non-IDP clusters | IDP clusters | Total target HHs (primary) | Accessible (Y/N) | Reason category | Reason notes | % of target achieved so far | Date reported | Reported by (Partner / IMPACT-default) | Source channel
Borno | Mafa | Mafa | Mafa | No |  |  | 2 | 2 | 126 | Yes | N/A - fully accessible | Source: FHI 360 point-level review (FHI 360_sampling_points_summary_FHI360.xlsx, Green/Red highlighting), shared by email 2026-08-17. All primary points in this ward marked Green (accessible). |  | 17/08/2026 | Partner | Point-level file annotation
Borno | Mafa | Gawa | Gawa | Yes | Dikwa | This ward's GRID3 polygon spans more than one LGA - you only need to report on the part of the ward that falls within your own LGA coverage. See the 'Other LGA(s) sharing this ward' column for where the rest of it sits. | 5 | 0 | 25 | No | Insecurity / conflict | Source: FHI 360 point-level review (FHI 360_sampling_points_summary_FHI360.xlsx, Green/Red highlighting), shared by email 2026-08-17. All primary points in this ward marked Red. Partner's own framing: "some of the assigned clusters and households are currently inaccessible, while others fall outside our approved movement boundaries" - not distinguished per ward in their email, so logged uniformly as Insecurity/conflict; flag to partner if a specific ward here is a movement-boundary case rather than active insecurity. | 0 | 17/08/2026 | Partner | Point-level file annotation
Borno | Mafa | Mujigine | Mujigine | No |  |  | 3 | 0 | 16 | No | Insecurity / conflict | Source: FHI 360 point-level review (FHI 360_sampling_points_summary_FHI360.xlsx, Green/Red highlighting), shared by email 2026-08-17. All primary points in this ward marked Red. Partner's own framing: "some of the assigned clusters and households are currently inaccessible, while others fall outside our approved movement boundaries" - not distinguished per ward in their email, so logged uniformly as Insecurity/conflict; flag to partner if a specific ward here is a movement-boundary case rather than active insecurity. | 0 | 17/08/2026 | Partner | Point-level file annotation
Borno | Mafa | Ajiri | Ajiri | Yes | Jere | This ward's GRID3 polygon spans more than one LGA - you only need to report on the part of the ward that falls within your own LGA coverage. See the 'Other LGA(s) sharing this ward' column for where the rest of it sits. | 3 | 0 | 13 | Yes | N/A - fully accessible | Partner updated Accessible to Yes on return (2026-09-13); SUPERSEDES the note below, which described this ward as Red/inaccessible per the Aug-17 point-level review. Original note: Source: FHI 360 point-level review (FHI 360_sampling_points_summary_FHI360.xlsx, Green/Red highlighting), shared by email 2026-08-17. All primary points in this ward marked Red. Partner's own framing: "some of the assigned clusters and households are currently inaccessible, while others fall outside our approved movement boundaries" - not distinguished per ward in their email, so logged uniformly as Insecurity/conflict; flag to partner if a specific ward here is a movement-boundary case rather than active insecurity. | 0 | 17/08/2026 | Partner | Point-level file annotation
Borno | Mafa | Koshebe | Koshebe | No |  |  | 2 | 0 | 8 | No | Insecurity / conflict | Source: FHI 360 point-level review (FHI 360_sampling_points_summary_FHI360.xlsx, Green/Red highlighting), shared by email 2026-08-17. All primary points in this ward marked Red. Partner's own framing: "some of the assigned clusters and households are currently inaccessible, while others fall outside our approved movement boundaries" - not distinguished per ward in their email, so logged uniformly as Insecurity/conflict; flag to partner if a specific ward here is a movement-boundary case rather than active insecurity. | 0 | 17/08/2026 | Partner | Point-level file annotation
Borno | Mafa | Laje | Lege | No |  |  | 1 | 0 | 6 | No | Insecurity / conflict | Source: FHI 360 point-level review (FHI 360_sampling_points_summary_FHI360.xlsx, Green/Red highlighting), shared by email 2026-08-17. All primary points in this ward marked Red. Partner's own framing: "some of the assigned clusters and households are currently inaccessible, while others fall outside our approved movement boundaries" - not distinguished per ward in their email, so logged uniformly as Insecurity/conflict; flag to partner if a specific ward here is a movement-boundary case rather than active insecurity. | 0 | 17/08/2026 | Partner | Point-level file annotation
Borno | Mafa | Masu | Masu | No |  |  | 1 | 0 | 4 | No | Insecurity / conflict | Source: FHI 360 point-level review (FHI 360_sampling_points_summary_FHI360.xlsx, Green/Red highlighting), shared by email 2026-08-17. All primary points in this ward marked Red. Partner's own framing: "some of the assigned clusters and households are currently inaccessible, while others fall outside our approved movement boundaries" - not distinguished per ward in their email, so logged uniformly as Insecurity/conflict; flag to partner if a specific ward here is a movement-boundary case rather than active insecurity. | 0 | 17/08/2026 | Partner | Point-level file annotation
Borno | Mafa | Limanti | Limanti | Yes | Bayo; Jere; Maiduguri | This ward's GRID3 polygon spans more than one LGA - you only need to report on the part of the ward that falls within your own LGA coverage. See the 'Other LGA(s) sharing this ward' column for where the rest of it sits. | 2 | 0 | 3 | No | Insecurity / conflict | Source: FHI 360 point-level review (FHI 360_sampling_points_summary_FHI360.xlsx, Green/Red highlighting), shared by email 2026-08-17. All primary points in this ward marked Red. Partner's own framing: "some of the assigned clusters and households are currently inaccessible, while others fall outside our approved movement boundaries" - not distinguished per ward in their email, so logged uniformly as Insecurity/conflict; flag to partner if a specific ward here is a movement-boundary case rather than active insecurity. | 0 | 17/08/2026 | Partner | Point-level file annotation
Borno | Mafa | Dalori | Tamsu Ngamdua | Yes | Jere; Konduga | This ward's GRID3 polygon spans more than one LGA - you only need to report on the part of the ward that falls within your own LGA coverage. See the 'Other LGA(s) sharing this ward' column for where the rest of it sits. | 1 | 0 | 2 | Yes | N/A - fully accessible | Source: FHI 360 point-level review (FHI 360_sampling_points_summary_FHI360.xlsx, Green/Red highlighting), shared by email 2026-08-17. All primary points in this ward marked Green (accessible). |  | 17/08/2026 | Partner | Point-level file annotation
Borno | Mafa | Khaddamari | Koshebe | No |  |  | 1 | 0 | 2 | No | Insecurity / conflict | Source: FHI 360 point-level review (FHI 360_sampling_points_summary_FHI360.xlsx, Green/Red highlighting), shared by email 2026-08-17. All primary points in this ward marked Red. Partner's own framing: "some of the assigned clusters and households are currently inaccessible, while others fall outside our approved movement boundaries" - not distinguished per ward in their email, so logged uniformly as Insecurity/conflict; flag to partner if a specific ward here is a movement-boundary case rather than active insecurity. | 0 | 17/08/2026 | Partner | Point-level file annotation
Borno | Mafa | Miye | Masu | Yes | Magumeri; Nganzai | This ward's GRID3 polygon spans more than one LGA - you only need to report on the part of the ward that falls within your own LGA coverage. See the 'Other LGA(s) sharing this ward' column for where the rest of it sits. | 1 | 0 | 2 | No | Insecurity / conflict | Source: FHI 360 point-level review (FHI 360_sampling_points_summary_FHI360.xlsx, Green/Red highlighting), shared by email 2026-08-17. All primary points in this ward marked Red. Partner's own framing: "some of the assigned clusters and households are currently inaccessible, while others fall outside our approved movement boundaries" - not distinguished per ward in their email, so logged uniformly as Insecurity/conflict; flag to partner if a specific ward here is a movement-boundary case rather than active insecurity. | 0 | 17/08/2026 | Partner | Point-level file annotation
Borno | Mafa | Tamsum Gamdua | Tamsu Ngamdua | Yes | Jere | This ward's GRID3 polygon spans more than one LGA - you only need to report on the part of the ward that falls within your own LGA coverage. See the 'Other LGA(s) sharing this ward' column for where the rest of it sits. | 1 | 0 | 2 | Yes | N/A - fully accessible | Source: FHI 360 point-level review (FHI 360_sampling_points_summary_FHI360.xlsx, Green/Red highlighting), shared by email 2026-08-17. All primary points in this ward marked Green (accessible). |  | 17/08/2026 | Partner | Point-level file annotation
Borno | Mobbar | Kareto | Kareto | No |  |  | 8 | 0 | 31 | No | Insecurity / conflict | Source: FHI 360 point-level review (FHI 360_sampling_points_summary_FHI360.xlsx, Green/Red highlighting), shared by email 2026-08-17. All primary points in this ward marked Red. Partner's email: "For Mobbar LGA, all currently assigned households are inaccessible." Partner proposed Damasak Town and Zanna Umarti as alternative accessible locations - neither is in FHI 360's currently assigned ward list, so this is a request for new supplementary point(s), not an existing point to mark accessible - needs a resampling-mechanism decision (draw-pool/stratum fit), not a template answer. | 0 | 17/08/2026 | Partner | Point-level file annotation
Borno | Mobbar | Layi | Chamba | No |  |  | 5 | 0 | 23 | No | Insecurity / conflict | Source: FHI 360 point-level review (FHI 360_sampling_points_summary_FHI360.xlsx, Green/Red highlighting), shared by email 2026-08-17. All primary points in this ward marked Red. Partner's email: "For Mobbar LGA, all currently assigned households are inaccessible." Partner proposed Damasak Town and Zanna Umarti as alternative accessible locations - neither is in FHI 360's currently assigned ward list, so this is a request for new supplementary point(s), not an existing point to mark accessible - needs a resampling-mechanism decision (draw-pool/stratum fit), not a template answer. | 0 | 17/08/2026 | Partner | Point-level file annotation
Borno | Mobbar | Futchimiram | Kareto | Yes | Gubio | This ward's GRID3 polygon spans more than one LGA - you only need to report on the part of the ward that falls within your own LGA coverage. See the 'Other LGA(s) sharing this ward' column for where the rest of it sits. | 3 | 0 | 15 | No | Insecurity / conflict | Source: FHI 360 point-level review (FHI 360_sampling_points_summary_FHI360.xlsx, Green/Red highlighting), shared by email 2026-08-17. All primary points in this ward marked Red. Partner's email: "For Mobbar LGA, all currently assigned households are inaccessible." Partner proposed Damasak Town and Zanna Umarti as alternative accessible locations - neither is in FHI 360's currently assigned ward list, so this is a request for new supplementary point(s), not an existing point to mark accessible - needs a resampling-mechanism decision (draw-pool/stratum fit), not a template answer. | 0 | 17/08/2026 | Partner | Point-level file annotation
Borno | Mobbar | Zari | Chamba | No |  |  | 2 | 0 | 11 | No | Insecurity / conflict | Source: FHI 360 point-level review (FHI 360_sampling_points_summary_FHI360.xlsx, Green/Red highlighting), shared by email 2026-08-17. All primary points in this ward marked Red. Partner's email: "For Mobbar LGA, all currently assigned households are inaccessible." Partner proposed Damasak Town and Zanna Umarti as alternative accessible locations - neither is in FHI 360's currently assigned ward list, so this is a request for new supplementary point(s), not an existing point to mark accessible - needs a resampling-mechanism decision (draw-pool/stratum fit), not a template answer. | 0 | 17/08/2026 | Partner | Point-level file annotation
Borno | Mobbar | Banowa | Bogum | Yes | Abadam; Kukawa | This ward's GRID3 polygon spans more than one LGA - you only need to report on the part of the ward that falls within your own LGA coverage. See the 'Other LGA(s) sharing this ward' column for where the rest of it sits. | 1 | 0 | 6 | No | Insecurity / conflict | Source: FHI 360 point-level review (FHI 360_sampling_points_summary_FHI360.xlsx, Green/Red highlighting), shared by email 2026-08-17. All primary points in this ward marked Red. Partner's email: "For Mobbar LGA, all currently assigned households are inaccessible." Partner proposed Damasak Town and Zanna Umarti as alternative accessible locations - neither is in FHI 360's currently assigned ward list, so this is a request for new supplementary point(s), not an existing point to mark accessible - needs a resampling-mechanism decision (draw-pool/stratum fit), not a template answer. | 0 | 17/08/2026 | Partner | Point-level file annotation
Borno | Mobbar | Gashigar | Gashigar | No |  |  | 1 | 0 | 6 | No | Insecurity / conflict | Source: FHI 360 point-level review (FHI 360_sampling_points_summary_FHI360.xlsx, Green/Red highlighting), shared by email 2026-08-17. All primary points in this ward marked Red. Partner's email: "For Mobbar LGA, all currently assigned households are inaccessible." Partner proposed Damasak Town and Zanna Umarti as alternative accessible locations - neither is in FHI 360's currently assigned ward list, so this is a request for new supplementary point(s), not an existing point to mark accessible - needs a resampling-mechanism decision (draw-pool/stratum fit), not a template answer. | 0 | 17/08/2026 | Partner | Point-level file annotation
Borno | Mobbar | Fukurti | Kareto | No |  |  | 2 | 0 | 5 | No | Insecurity / conflict | Source: FHI 360 point-level review (FHI 360_sampling_points_summary_FHI360.xlsx, Green/Red highlighting), shared by email 2026-08-17. All primary points in this ward marked Red. Partner's email: "For Mobbar LGA, all currently assigned households are inaccessible." Partner proposed Damasak Town and Zanna Umarti as alternative accessible locations - neither is in FHI 360's currently assigned ward list, so this is a request for new supplementary point(s), not an existing point to mark accessible - needs a resampling-mechanism decision (draw-pool/stratum fit), not a template answer. | 0 | 17/08/2026 | Partner | Point-level file annotation
Borno | Mobbar | Ngetra | Kareto | Yes | Gubio | This ward's GRID3 polygon spans more than one LGA - you only need to report on the part of the ward that falls within your own LGA coverage. See the 'Other LGA(s) sharing this ward' column for where the rest of it sits. | 2 | 0 | 4 | No | Insecurity / conflict | Source: FHI 360 point-level review (FHI 360_sampling_points_summary_FHI360.xlsx, Green/Red highlighting), shared by email 2026-08-17. All primary points in this ward marked Red. Partner's email: "For Mobbar LGA, all currently assigned households are inaccessible." Partner proposed Damasak Town and Zanna Umarti as alternative accessible locations - neither is in FHI 360's currently assigned ward list, so this is a request for new supplementary point(s), not an existing point to mark accessible - needs a resampling-mechanism decision (draw-pool/stratum fit), not a template answer. | 0 | 17/08/2026 | Partner | Point-level file annotation
Borno | Mobbar | Chamba | Chamba | No |  |  | 1 | 0 | 1 | No | Insecurity / conflict | Source: FHI 360 point-level review (FHI 360_sampling_points_summary_FHI360.xlsx, Green/Red highlighting), shared by email 2026-08-17. All primary points in this ward marked Red. Partner's email: "For Mobbar LGA, all currently assigned households are inaccessible." Partner proposed Damasak Town and Zanna Umarti as alternative accessible locations - neither is in FHI 360's currently assigned ward list, so this is a request for new supplementary point(s), not an existing point to mark accessible - needs a resampling-mechanism decision (draw-pool/stratum fit), not a template answer. | 0 | 17/08/2026 | Partner | Point-level file annotation
Borno | Mobbar | Gazabure | Chamba | Yes | Gubio | This ward's GRID3 polygon spans more than one LGA - you only need to report on the part of the ward that falls within your own LGA coverage. See the 'Other LGA(s) sharing this ward' column for where the rest of it sits. | 1 | 0 | 0 | No | Insecurity / conflict | Not individually marked in the partner's file (zero primary target HHs here - reserve-only ward), but included for consistency with the rest of Mobbar per the partner's blanket "all currently assigned households are inaccessible" statement. No practical effect since there's no primary sample here. | 0 | 17/08/2026 | Partner | Email
Borno | Mafa | Loskuri | Loskuri |  |  |  | 5 | 0 | 24 | No | Insecurity / conflict | Reported inaccessible by FHI 360 via email, 2026-09-09 - please confirm Accessible=No and pick a reason category. |  |  | Partner | Partner's own template
Borno | Mafa | Ma'Afa | Ma'Afa |  |  |  | 4 | 0 | 16 | No | Insecurity / conflict | Reported inaccessible by FHI 360 via email, 2026-09-09 - please confirm Accessible=No and pick a reason category. |  |  | Partner | Partner's own template
Borno | Mafa | Mofio | Masu |  |  |  | 2 | 0 | 9 | No | Insecurity / conflict | Reported inaccessible by FHI 360 via email, 2026-09-09 - please confirm Accessible=No and pick a reason category. |  |  | Partner | Partner's own template
Borno | Mafa | Zengebe | Zangebe |  |  |  | 2 | 0 | 7 | No | Insecurity / conflict | Reported inaccessible by FHI 360 via email, 2026-09-09 - please confirm Accessible=No and pick a reason category. |  |  | Partner | Partner's own template
Borno | Mafa | Maiwa | Masu |  |  |  | 1 | 0 | 3 | No | Insecurity / conflict | Reported inaccessible by FHI 360 via email, 2026-09-09 - please confirm Accessible=No and pick a reason category. |  |  | Partner | Partner's own template
Borno | Mobbar | Zanna Umarti | Zulum Umarti |  |  |  | 14 | 5 | 132 | Yes | N/A - fully accessible |  |  |  | Partner | Partner's own template
Borno | Mobbar | Damasak | Damasak |  |  |  | 3 | 5 | 76 | Yes | N/A - fully accessible |  |  |  | Partner | Partner's own template

## Cluster Accessibility
State | LGA | Ward (GRID3) | Pop Type | Cluster ID | IDP Category | Target HHs (primary) | Reserve HHs | Accessible (Y/N) | Reason category | Reason notes | % of target achieved so far | Date reported | Reported by (Partner / IMPACT-default) | Source channel
Borno | Mafa | Mafa | IDP | idp_NG008019_1 | In-camp | 96 | 96
Borno | Mafa | Mafa | IDP | idp_NG008019_17 | In-host | 6 | 6
Borno | Mafa | Masu | Non-IDP | non_idp_NG008019_1 |  | 6 | 6
Borno | Mafa | Mujigine | Non-IDP | non_idp_NG008019_10 |  | 6 | 6
Borno | Mafa | Ajiri | Non-IDP | non_idp_NG008019_11 |  | 6 | 6
Borno | Mafa | Mujigine | Non-IDP | non_idp_NG008019_12 |  | 6 | 6
Borno | Mafa | Limanti | Non-IDP | non_idp_NG008019_13 |  | 6 | 6
Borno | Mafa | Koshebe | Non-IDP | non_idp_NG008019_14 |  | 6 | 6
Borno | Mafa | Limanti | Non-IDP | non_idp_NG008019_15 |  | 6 | 6
Borno | Mafa | Gawa | Non-IDP | non_idp_NG008019_16 |  | 6 | 6
Borno | Mafa | Khaddamari | Non-IDP | non_idp_NG008019_17 |  | 6 | 6
Borno | Mafa | Mafa | Non-IDP | non_idp_NG008019_2 |  | 12 | 12
Borno | Mafa | Mafa | Non-IDP | non_idp_NG008019_4 |  | 12 | 12
Borno | Mafa | Ajiri | Non-IDP | non_idp_NG008019_6 |  | 6 | 6
Borno | Mafa | Ajiri | Non-IDP | non_idp_NG008019_7 |  | 6 | 6
Borno | Mafa | Mujigine | Non-IDP | non_idp_NG008019_8 |  | 6 | 6
Borno | Mafa | Gawa | Non-IDP | non_idp_NG008019_9 |  | 6 | 6
Borno | Mafa | Gawa | Non-IDP | non_idp_NG008019_supp1 |  | 6 | 6
Borno | Mafa | Gawa | Non-IDP | non_idp_NG008019_supp2 |  | 6 | 6
Borno | Mafa | Tamsum Gamdua | Non-IDP | non_idp_NG008019_supp3 |  | 6 | 6
Borno | Mafa | Gawa | Non-IDP | non_idp_NG008019_supp4 |  | 6 | 6
Borno | Mafa | Laje | Non-IDP | non_idp_NG008019_supp5 |  | 6 | 6
Borno | Mobbar | Layi | Non-IDP | non_idp_NG008023_1 |  | 6 | 6
Borno | Mobbar | Futchimiram | Non-IDP | non_idp_NG008023_10 |  | 6 | 6
Borno | Mobbar | Kareto | Non-IDP | non_idp_NG008023_11 |  | 6 | 6
Borno | Mobbar | Kareto | Non-IDP | non_idp_NG008023_12 |  | 6 | 6
Borno | Mobbar | Kareto | Non-IDP | non_idp_NG008023_13 |  | 6 | 6
Borno | Mobbar | Layi | Non-IDP | non_idp_NG008023_14 |  | 6 | 6
Borno | Mobbar | Kareto | Non-IDP | non_idp_NG008023_15 |  | 6 | 6
Borno | Mobbar | Layi | Non-IDP | non_idp_NG008023_16 |  | 6 | 6
Borno | Mobbar | Layi | Non-IDP | non_idp_NG008023_17 |  | 6 | 6
Borno | Mobbar | Layi | Non-IDP | non_idp_NG008023_2 |  | 6 | 6
Borno | Mobbar | Zari | Non-IDP | non_idp_NG008023_3 |  | 6 | 6
Borno | Mobbar | Zari | Non-IDP | non_idp_NG008023_4 |  | 6 | 6
Borno | Mobbar | Kareto | Non-IDP | non_idp_NG008023_5 |  | 6 | 6
Borno | Mobbar | Gashigar | Non-IDP | non_idp_NG008023_6 |  | 6 | 6
Borno | Mobbar | Kareto | Non-IDP | non_idp_NG008023_7 |  | 6 | 6
Borno | Mobbar | Banowa | Non-IDP | non_idp_NG008023_8 |  | 6 | 6
Borno | Mobbar | Futchimiram | Non-IDP | non_idp_NG008023_9 |  | 6 | 6