## README
Street Child of Nigeria - NGA MSNA 2026 accessibility report
Overview
This file lists every ward (and, on the second sheet, every individual cluster) currently assigned to your organisation under the NGA MSNA 2026 sampling design, so you can tell us where your teams are having trouble collecting data and why. We use this to decide how to respond - drawing a replacement cluster where needed - and to correctly document, in our final reporting, which areas' we were able to collect from and which we weren't. Accurate, complete reporting from you feeds directly into that documentation.
Assigned to you: 26 wards, 58 clusters
What to do
1 | Open the 'Ward Accessibility' sheet first - this is your main report, one row per ward you have clusters in. It's pre-filled with every ward/LGA combination assigned to you; you don't need to add or remove rows. Rows are sorted within each LGA by Total target HHs, largest first, so your main wards come before any small border cases.
2 | A row with a very small Total target HHs figure (1-2) usually means a border case - GRID3 and OCHA/COD boundaries don't always agree exactly, so a small part of one of your clusters can fall just inside a ward you don't otherwise work in. This is expected, not an error - please still report on it like any other row if it's genuinely inaccessible. If a row also shows 'Yes' under 'Ward spans multiple LGAs', see that row's Note for what part of the ward is actually yours to report on.
3 | For each ward, set Accessible (Y/N). Leave a ward's row otherwise blank if there's no issue there.
4 | For any ward marked 'No', pick the closest-fitting Reason category from the dropdown (use 'Other' plus a note if none fit), and add specific Reason notes - e.g. 'active clashes reported near [location] in the past week' is far more useful to us than just 'insecure'.
5 | If you know it, fill in roughly what % of the target sample you were able to achieve in that ward before stopping - even a rough estimate helps, and please don't leave this blank if the true answer is 0%.
6 | The last two columns ('Reported by' and 'Source channel') are for our own internal record-keeping - please leave them blank unless we've asked you to fill in a specific row on our behalf (e.g. transcribing a WhatsApp/verbal report into this sheet).
7 | Only use the 'Cluster Accessibility' sheet (second tab) for a problem specific to ONE site/HH within an otherwise-fine ward - and only once you've already worked through that cluster's reserve/replacement households and they weren't enough to cover it. Don't use this sheet before exhausting your reserve list for that cluster, and don't use it as a second way to report the same ward-wide issue already captured on the first sheet.
8 | Date reported must be an actual date, not typed text - click the cell and use Excel's date picker, or type it as e.g. 27-Aug-2026. The cell will reject anything that isn't a real date, or a date before 01 Jul 2026/after today.
9 | IMPORTANT: please review your ENTIRE coverage area in one pass before sending this back to us, rather than reporting a few wards now and more later - this significantly cuts down the back-and-forth rounds we need with you. If genuinely new information comes in afterwards, send an updated copy of the FULL sheet (not just the changed rows) with a new Date reported - we track changes over time by date, so we don't need you to tell us what changed, just the current full picture.
Which sheet do I use?
Sheet | Use for
Ward Accessibility | Your main report. Use for any access problem affecting a ward generally - insecurity, flooding/terrain, population displacement, denied access, etc.
Cluster Accessibility | Secondary/detail only. Use ONLY for a problem specific to one site/HH, not the surrounding ward, and only after that cluster's reserve/replacement households were already used and weren't enough.

## Ward Accessibility
State | LGA | Ward (GRID3) | Ward (OCHA/COD) | Ward spans multiple LGAs (Y/N) | Other LGA(s) sharing this ward | Note | Non-IDP clusters | IDP clusters | Total target HHs (primary) | Accessible (Y/N) | Reason category | Reason notes | % of target achieved so far | Date reported | Reported by (Partner / IMPACT-default) | Source channel
Adamawa | Madagali | Gulak | Gulak | No |  |  | 5 | 2 | 66 | No
Adamawa | Madagali | Madagali | Madagali | No |  |  | 2 | 3 | 31 | Yes
Adamawa | Madagali | Sukur | Sukur | No |  |  | 2 | 2 | 25 | No | Physical access (terrain
Adamawa | Madagali | Pallam | Pallam | No |  |  | 1 | 2 | 24 | No | Physical access (terrain
Adamawa | Madagali | Waga-Chakawa | Waga-chakawa | No |  |  | 2 | 1 | 18 | No
Adamawa | Madagali | Hyambula | Hyambula | No |  |  | 3 | 1 | 14 | No
Adamawa | Madagali | Duhu | Duhu | No |  |  | 3 | 0 | 13 | No | Physical access (terrain
Adamawa | Madagali | Bita Izge | Gulak | No |  |  | 2 | 0 | 6 | No
Adamawa | Madagali | Bebel | Bebel | No |  |  | 1 | 0 | 5 | No
Adamawa | Madagali | Kirchinga | Kirchinga | No |  |  | 1 | 0 | 2 | No | Insecurity / conflict
Borno | Monguno | Monguno | Kumalia | Yes | Guzamala | This ward's GRID3 polygon spans more than one LGA - you only need to report on the part of the ward that falls within your own LGA coverage. See the 'Other LGA(s) sharing this ward' column for where the rest of it sits. | 3 | 3 | 162 | Yes
Borno | Monguno | Wulo | Wulo | No |  |  | 3 | 0 | 18 | No | Population absent / relocated
Borno | Monguno | Mintar | Mintar | No |  |  | 2 | 0 | 10 | No | Population absent / relocated
Borno | Monguno | Kekeno | Ngurno | Yes | Kukawa | This ward's GRID3 polygon spans more than one LGA - you only need to report on the part of the ward that falls within your own LGA coverage. See the 'Other LGA(s) sharing this ward' column for where the rest of it sits. | 1 | 0 | 6 | Yes | N/A - fully accessible | Corrected 2026-09-16: cell said No but the ward name was highlighted yellow in the returned file, matching Monguno ward's own highlight - both meant to mark the 2 real accessible Monguno wards. Data-entry slip, not new information.
Borno | Monguno | Mofio | Damakuli | No |  |  | 2 | 0 | 5 | No | Population absent / relocated |  |  |  | Partner | WhatsApp/verbal (coordinator-transcribed)
Borno | Monguno | Sure | Sure | No |  |  | 1 | 0 | 3 | No | Population absent / relocated |  |  |  | Partner | WhatsApp/verbal (coordinator-transcribed)
Borno | Monguno | Kaguram | Mintar | No |  |  | 1 | 0 | 2 | No | Population absent / relocated |  |  |  | Partner | WhatsApp/verbal (coordinator-transcribed)
Adamawa | Madagali | Wula |  | No |  | Newly added 2026-09-16 - not previously listed. | 0 | 0 | 0 | No | Insecurity / conflict |  |  |  | Partner | WhatsApp/verbal (coordinator-transcribed)
Borno | Monguno | Damakulli |  | No |  | Newly added 2026-09-16 - not previously listed. | 0 | 0 | 0 | No | Insecurity / conflict |  |  |  | Partner | WhatsApp/verbal (coordinator-transcribed)
Borno | Monguno | Kumalia |  | No |  | Newly added 2026-09-16 - not previously listed. | 0 | 0 | 0 | No | Insecurity / conflict |  |  |  | Partner | WhatsApp/verbal (coordinator-transcribed)
Borno | Monguno | Mandala |  | No |  | Newly added 2026-09-16 - not previously listed. | 0 | 0 | 0 | No | Insecurity / conflict |  |  |  | Partner | WhatsApp/verbal (coordinator-transcribed)
Borno | Monguno | Ngurno |  | No |  | Newly added 2026-09-16 - not previously listed. | 0 | 0 | 0 | No | Insecurity / conflict |  |  |  | Partner | WhatsApp/verbal (coordinator-transcribed)
Borno | Monguno | Yele |  | No |  | Newly added 2026-09-16 - not previously listed. | 0 | 0 | 0 | No | Insecurity / conflict |  |  |  | Partner | WhatsApp/verbal (coordinator-transcribed)
Borno | Monguno | Zulum |  | No |  | Newly added 2026-09-16 - not previously listed. | 0 | 0 | 0 | No | Insecurity / conflict |  |  |  | Partner | WhatsApp/verbal (coordinator-transcribed)
Borno | Monguno | Yoyo | Kumalia | Yes | Kukawa | Newly added 2026-09-16 - not previously listed. This ward's GRID3 polygon spans more than one LGA - you only need to report on the part of the ward that falls within your own LGA coverage. See the 'Other LGA(s) sharing this ward' column for where the rest of it sits. | 1 | 0 | 2 | No | Insecurity / conflict |  |  |  | Partner | WhatsApp/verbal (coordinator-transcribed)
Adamawa | Madagali | Garta |  | Yes | Michika | Newly added 2026-09-20 - this ward is Stage-1-eligible for your coverage but had never had a cluster drawn in it by chance, so it was missing from your assignment list until now (a gap found and fixed today, see the accompanying email). Please review and report on it like any other row. | 0 | 0 | 0 | No | Insecurity / conflict |  |  |  | Partner | WhatsApp/verbal (coordinator-transcribed)
Adamawa | Madagali | Hambagda Limankara Jaje |  | No |  | Newly added 2026-09-20 - this ward is Stage-1-eligible for your coverage but had never had a cluster drawn in it by chance, so it was missing from your assignment list until now (a gap found and fixed today, see the accompanying email). Please review and report on it like any other row. | 0 | 0 | 0 | No | Insecurity / conflict |  |  |  | Partner | WhatsApp/verbal (coordinator-transcribed)
Adamawa | Madagali | Ngurthavu Kopa |  | Yes | Michika | Newly added 2026-09-20 - this ward is Stage-1-eligible for your coverage but had never had a cluster drawn in it by chance, so it was missing from your assignment list until now (a gap found and fixed today, see the accompanying email). Please review and report on it like any other row. | 0 | 0 | 0 | No | Insecurity / conflict |  |  |  | Partner | WhatsApp/verbal (coordinator-transcribed)
Adamawa | Madagali | Ninkisi / Wuro Ngiki |  | Yes | Michika | Newly added 2026-09-20 - this ward is Stage-1-eligible for your coverage but had never had a cluster drawn in it by chance, so it was missing from your assignment list until now (a gap found and fixed today, see the accompanying email). Please review and report on it like any other row. | 0 | 0 | 0 | No | Insecurity / conflict |  |  |  | Partner | WhatsApp/verbal (coordinator-transcribed)
Adamawa | Madagali | Tumbara / Ngabili |  | Yes | Michika | Newly added 2026-09-20 - this ward is Stage-1-eligible for your coverage but had never had a cluster drawn in it by chance, so it was missing from your assignment list until now (a gap found and fixed today, see the accompanying email). Please review and report on it like any other row. | 0 | 0 | 0 | No | Insecurity / conflict |  |  |  | Partner | WhatsApp/verbal (coordinator-transcribed)
Borno | Monguno | Alarge |  | Yes | Guzamala; Nganzai | Newly added 2026-09-20 - this ward is Stage-1-eligible for your coverage but had never had a cluster drawn in it by chance, so it was missing from your assignment list until now (a gap found and fixed today, see the accompanying email). Please review and report on it like any other row. | 0 | 0 | 0 | No | Insecurity / conflict |  |  |  | Partner | WhatsApp/verbal (coordinator-transcribed)
Borno | Monguno | Badairi |  | No |  | Newly added 2026-09-20 - this ward is Stage-1-eligible for your coverage but had never had a cluster drawn in it by chance, so it was missing from your assignment list until now (a gap found and fixed today, see the accompanying email). Please review and report on it like any other row. | 0 | 0 | 0 | No | Insecurity / conflict |  |  |  | Partner | WhatsApp/verbal (coordinator-transcribed)
Borno | Monguno | Kabulawa |  | Yes | Mafa | Newly added 2026-09-20 - this ward is Stage-1-eligible for your coverage but had never had a cluster drawn in it by chance, so it was missing from your assignment list until now (a gap found and fixed today, see the accompanying email). Please review and report on it like any other row. | 0 | 0 | 0 | No | Insecurity / conflict |  |  |  | Partner | WhatsApp/verbal (coordinator-transcribed)
Borno | Monguno | Kingarwa |  | Yes | Guzamala | Newly added 2026-09-20 - this ward is Stage-1-eligible for your coverage but had never had a cluster drawn in it by chance, so it was missing from your assignment list until now (a gap found and fixed today, see the accompanying email). Please review and report on it like any other row. | 0 | 0 | 0 | No | Insecurity / conflict |  |  |  | Partner | WhatsApp/verbal (coordinator-transcribed)
Borno | Monguno | Kirenowa |  | No |  | Newly added 2026-09-20 - this ward is Stage-1-eligible for your coverage but had never had a cluster drawn in it by chance, so it was missing from your assignment list until now (a gap found and fixed today, see the accompanying email). Please review and report on it like any other row. | 0 | 0 | 0 | No | Insecurity / conflict |  |  |  | Partner | WhatsApp/verbal (coordinator-transcribed)
Borno | Monguno | Maiwa |  | Yes | Mafa; Nganzai | Newly added 2026-09-20 - this ward is Stage-1-eligible for your coverage but had never had a cluster drawn in it by chance, so it was missing from your assignment list until now (a gap found and fixed today, see the accompanying email). Please review and report on it like any other row. | 0 | 0 | 0 | No | Insecurity / conflict |  |  |  | Partner | WhatsApp/verbal (coordinator-transcribed)
Borno | Monguno | Masu |  | Yes | Jere; Mafa; Nganzai | Newly added 2026-09-20 - this ward is Stage-1-eligible for your coverage but had never had a cluster drawn in it by chance, so it was missing from your assignment list until now (a gap found and fixed today, see the accompanying email). Please review and report on it like any other row. | 0 | 0 | 0 | No | Insecurity / conflict |  |  |  | Partner | WhatsApp/verbal (coordinator-transcribed)
Borno | Monguno | Sugundure |  | Yes | Nganzai | Newly added 2026-09-20 - this ward is Stage-1-eligible for your coverage but had never had a cluster drawn in it by chance, so it was missing from your assignment list until now (a gap found and fixed today, see the accompanying email). Please review and report on it like any other row. | 0 | 0 | 0 | No | Insecurity / conflict |  |  |  | Partner | WhatsApp/verbal (coordinator-transcribed)

## Cluster Accessibility
State | LGA | Ward (GRID3) | Pop Type | Cluster ID | IDP Category | Target HHs (primary) | Reserve HHs | Accessible (Y/N) | Reason category | Reason notes | % of target achieved so far | Date reported | Reported by (Partner / IMPACT-default) | Source channel
Adamawa | Madagali | Gulak | IDP | idp_NG002010_1 | In-host | 30 | 30
Adamawa | Madagali | Pallam | IDP | idp_NG002010_10 | In-host | 6 | 6
Adamawa | Madagali | Sukur | IDP | idp_NG002010_11 | In-host | 6 | 6
Adamawa | Madagali | Waga-Chakawa | IDP | idp_NG002010_12 | In-host | 6 | 6
Adamawa | Madagali | Sukur | IDP | idp_NG002010_13 | In-host | 12 | 12
Adamawa | Madagali | Madagali | IDP | idp_NG002010_15 | In-host | 6 | 6
Adamawa | Madagali | Madagali | IDP | idp_NG002010_16 | In-host | 6 | 6
Adamawa | Madagali | Madagali | IDP | idp_NG002010_17 | In-host | 6 | 6
Adamawa | Madagali | Gulak | IDP | idp_NG002010_6 | In-host | 6 | 6
Adamawa | Madagali | Pallam | IDP | idp_NG002010_7 | In-host | 12 | 12
Adamawa | Madagali | Hyambula | IDP | idp_NG002010_9 | In-host | 6 | 6
Adamawa | Madagali | Gulak | Non-IDP | non_idp_NG002010_1 |  | 6 | 6
Adamawa | Madagali | Hyambula | Non-IDP | non_idp_NG002010_10 |  | 6 | 6
Adamawa | Madagali | Waga-Chakawa | Non-IDP | non_idp_NG002010_11 |  | 6 | 6
Adamawa | Madagali | Sukur | Non-IDP | non_idp_NG002010_12 |  | 6 | 6
Adamawa | Madagali | Bebel | Non-IDP | non_idp_NG002010_13 |  | 6 | 6
Adamawa | Madagali | Bita Izge | Non-IDP | non_idp_NG002010_14 |  | 6 | 6
Adamawa | Madagali | Madagali | Non-IDP | non_idp_NG002010_15 |  | 12 | 12
Adamawa | Madagali | Waga-Chakawa | Non-IDP | non_idp_NG002010_17 |  | 6 | 6
Adamawa | Madagali | Duhu | Non-IDP | non_idp_NG002010_2 |  | 6 | 6
Adamawa | Madagali | Gulak | Non-IDP | non_idp_NG002010_3 |  | 6 | 6
Adamawa | Madagali | Gulak | Non-IDP | non_idp_NG002010_4 |  | 12 | 12
Adamawa | Madagali | Duhu | Non-IDP | non_idp_NG002010_6 |  | 6 | 6
Adamawa | Madagali | Gulak | Non-IDP | non_idp_NG002010_7 |  | 6 | 6
Adamawa | Madagali | Hyambula | Non-IDP | non_idp_NG002010_8 |  | 6 | 6
Adamawa | Madagali | Pallam | Non-IDP | non_idp_NG002010_9 |  | 6 | 6
Borno | Monguno | Monguno | IDP | idp_NG008024_1 | In-camp | 24 | 24
Borno | Monguno | Monguno | IDP | idp_NG008024_10 | In-camp | 48 | 48
Borno | Monguno | Monguno | IDP | idp_NG008024_5 | In-camp | 30 | 30
Borno | Monguno | Mintar | Non-IDP | non_idp_NG008024_1 |  | 6 | 6
Borno | Monguno | Monguno | Non-IDP | non_idp_NG008024_11 |  | 36 | 36
Borno | Monguno | Mofio | Non-IDP | non_idp_NG008024_17 |  | 6 | 6
Borno | Monguno | Kekeno | Non-IDP | non_idp_NG008024_2 |  | 6 | 6 | Yes | N/A - fully accessible
Borno | Monguno | Mofio | Non-IDP | non_idp_NG008024_3 |  | 6 | 6
Borno | Monguno | Wulo | Non-IDP | non_idp_NG008024_4 |  | 6 | 6
Borno | Monguno | Wulo | Non-IDP | non_idp_NG008024_5 |  | 6 | 6
Borno | Monguno | Mintar | Non-IDP | non_idp_NG008024_6 |  | 6 | 6
Borno | Monguno | Monguno | Non-IDP | non_idp_NG008024_7 |  | 12 | 12
Borno | Monguno | Monguno | Non-IDP | non_idp_NG008024_9 |  | 12 | 12
Borno | Monguno | Sure | Non-IDP | non_idp_NG008024_supp1 |  | 6 | 6
Borno | Monguno | Wulo | Non-IDP | non_idp_NG008024_supp2 |  | 6 | 6
Borno | Monguno | Monguno | Non-IDP | non_idp_NG008024_supp3 |  | 6 | 6
Adamawa | Madagali | Gulak | Non-IDP | non_idp_NG002010_supp1 |  | 6 | 6
Adamawa | Madagali | Gulak | Non-IDP | non_idp_NG002010_supp2 |  | 6 | 6
Adamawa | Madagali | Gulak | Non-IDP | non_idp_NG002010_supp4 |  | 6 | 6
Adamawa | Madagali | Gulak | Non-IDP | non_idp_NG002010_supp9 |  | 6 | 6
Borno | Monguno | Kekeno | Non-IDP | non_idp_NG008024_supp19 |  | 6 | 6
Adamawa | Madagali | Gulak | Non-IDP | non_idp_NG002010_supp11 |  | 6 | 6
Adamawa | Madagali | Gulak | Non-IDP | non_idp_NG002010_supp12 |  | 6 | 6
Adamawa | Madagali | Gulak | Non-IDP | non_idp_NG002010_supp13 |  | 6 | 6
Borno | Monguno | Monguno | Non-IDP | non_idp_NG008024_supp26 |  | 6 | 6
Borno | Monguno | Monguno | Non-IDP | non_idp_NG008024_supp27 |  | 6 | 6
Borno | Monguno | Monguno | Non-IDP | non_idp_NG008024_supp28 |  | 6 | 6
Borno | Monguno | Monguno | Non-IDP | non_idp_NG008024_supp29 |  | 6 | 6
Borno | Monguno | Monguno | Non-IDP | non_idp_NG008024_supp30 |  | 6 | 6
Adamawa | Madagali | Gulak | Non-IDP | non_idp_NG002010_supp14 |  | 6 | 6
Adamawa | Madagali | Gulak | Non-IDP | non_idp_NG002010_supp16 |  | 6 | 6
Adamawa | Madagali | Gulak | IDP | idp_NG002010_supp1 | In-host | 12 | 12
Adamawa | Madagali | Gulak | IDP | idp_NG002010_supp2 | In-host | 6 | 6
Adamawa | Madagali | Gulak | IDP | idp_NG002010_supp3 | In-host | 6 | 6
Borno | Monguno | Monguno | IDP | idp_NG008024_supp1 | In-camp | 6 | 6
Borno | Monguno | Monguno | IDP | idp_NG008024_supp10 | In-camp | 6 | 6
Borno | Monguno | Monguno | IDP | idp_NG008024_supp11 | In-camp | 6 | 6
Borno | Monguno | Monguno | IDP | idp_NG008024_supp2 | In-host | 6 | 6
Borno | Monguno | Monguno | IDP | idp_NG008024_supp3 | In-host | 6 | 6
Borno | Monguno | Monguno | IDP | idp_NG008024_supp4 | In-host | 6 | 6
Borno | Monguno | Monguno | IDP | idp_NG008024_supp5 | In-host | 6 | 6
Borno | Monguno | Monguno | IDP | idp_NG008024_supp6 | In-host | 6 | 6
Borno | Monguno | Monguno | IDP | idp_NG008024_supp7 | In-camp | 6 | 6
Borno | Monguno | Monguno | IDP | idp_NG008024_supp8 | In-host | 6 | 6
Borno | Monguno | Monguno | IDP | idp_NG008024_supp9 | In-host | 6 | 6
Borno | Monguno | Monguno | Non-IDP | non_idp_NG008024_supp31 |  | 6 | 6
Borno | Monguno | Monguno | Non-IDP | non_idp_NG008024_supp32 |  | 6 | 6